## Sheet1
coverpage
Acknowledgement | 3
Abstract | 4
Add Table of Contents here
1 | Introduction | 7
1.1 | Background Studies | 7
1.2 | Problem Statement | 9
1.3 | Objective | 12
1.4 | Solutions | 15
2.0 Literature Review | 23
Literature Review: Sri Lankan Cuisine, Digital Platforms, and Technological Integration | 23
Sri Lankan Cuisine and its Cultural Significance | 23
The Role of Digital Technologies in Culinary Discovery | 30
Challenges in Personalized User Engagement and Scalability | 31
Challenges in Local Seller Digital Transformation | 31
Analyzing strengths and weaknesses | 32
Methodologies | 38
3.0 Planning | 44
3.0.1 Feasibility Report | 44
3.0.2 Risk Assessment | 49
3.0.3 SWOT | 55
3.0.4 PESTAL Analysis | 60
3.0.5 Life Cycle Model | 66
3.1.1 Time Plan | 72
4.2Requirement Gathering and Analysis | 80
4.2.2 Questioner | 84
4.2.3 Interview | 89
Summary of the Interview and Questionnaire | 91
4.3 Functional and Non-Functional Requirements | 93
4.3.1 Functional Requirements | 93
4.3.2 Non-functional Requirement | 98
5.0 System Design | 103
5.1 Architecture Diagram | 103
5.2 ER Diagram | 108
5.3 UML Diagrams | 109
6.0 Implementation | 120
6.1 Technology Stack | 120
6.2 Design patterns | 122
6.3 Implementation of the program | 129
Ingredient Detection System | 129
Recipe Suggestion Expert System | 137
Shop | 144
7.0 Testing and Validation | 176
Test Plan | 176
Test Cases | 178
8.0 Conclusion | 200
8.1 Conclusion | 200
8.2 Future Recommendations | 201
8.3 Lessons Learned | 203
Gantt Chart | 205
References | 206
Plagiarism Report | 207
Project Access links | 208
Appendices | 209
Dataset Training | 209
Dataset Testing | 210
Dataset | 211
Requirements Gathering Forms | 212
Requirements | 214
Source Codes | 216

## Sheet2
From date | To date | Work in progress | For next week
2025-07-03 | 2025-07-14 | Project proposal submitted | Proposal literatuer review and game idea
2025-07-14 | 2025-07-21 | Proposal literatuer review and game idea | Add more details to literature review, describe the game idea details more
2025-07-21 | 2025-07-28 | Add more details to literature review, describe the game idea details more | Select a game development model and describe it. Add more research paper details to the difference SQL lerning platforms
2025-07-28 | 2025-07-31 | Submitted a game development model and describe it. Submited more research paper details to the difference SQL lerning platforms | Summarize a different sql learning platform details. Combine both selected game development model and game idea and createe a document. Add a coclusion to the litratuere review.
2025-07-31 | 2025-08-04 | Literature review submitted | Add a game story to the game idea. Select a one level of game scenario and describe it.
2025-08-04 | 2025-08-20 | Added a game story to the game idea. Selected a one level of game scenario and describe it. | Make a prototype model for one game scenario.
2025-08-20 | 2025-08-24 | Made a prototype model for game 1 scenario. | Add a game scenario idea flow to the one scenario. Add different outcome errors get different hints.
2025-08-24 | 2025-08-28 | Added a game scenario ida flow to that one scenario. | Show the ssql database in page bottom and add a next button when nsql quires appear. Add help page different outcomes has different answers.
2025-08-28 | 2025-08-31 | Final document submitted | Add Game reset and help section.

## Sheet3
From Date | To Date | Work in Progress | For Next Week
2025-07-03 | 2025-07-14 | Project proposal submitted. | Prepare proposal literature review and game idea.
2025-07-14 | 2025-07-21 | Completed proposal literature review and outlined the game idea. | Add more details to the literature review and expand on the game idea description.
2025-07-21 | 2025-07-28 | Added more details to the literature review and described the game idea in depth. | Select a game development model and describe it.Add more research details on existing SQL learning platforms.
2025-07-28 | 2025-07-31 | Submitted a game development model description.Added more research details on SQL learning platforms. | Summarize a different SQL learning platform.Combine both selected game development model and game idea into a document.Add a conclusion to the literature review.
2025-07-31 | 2025-08-04 | Literature review submitted. | Add a storyline to the game idea.Select one level of the game scenario and describe it.
2025-08-04 | 2025-08-20 | Added a storyline to the game idea.Selected one level of the game scenario and described it. | Build a prototype model for one game scenario.Add a scenario flow with outcomes.Introduce hints for different error outcomes.
2025-08-20 | 2025-08-24 | Developed a prototype model for the first game scenario. | Add a scenario flow to the prototype.Ensure different error outcomes provide specific hints.
2025-08-24 | 2025-08-28 | Expanded the scenario flow for the prototype.Added variations for different outcomes. | Display the SQL database at the bottom of the page.Add a “Next” button for when no SQL query appears.Create a help page with guidance for different outcomes.
2025-08-28 | 2025-08-31 | Final project document submitted. | Add game reset functionality and finalize the help section.

## Sheet4
Features | Objective | Scope | Test Type
User Authentication | Verify login/register works correctly. | Test if users can sign up, log in, and maintain sessions securely. | Functional testing, Security testing
Auto-Scroll & Character Introduction | Ensure smooth introduction sequence on landing page. | Check auto-scroll animations, character display, and text narration. | Usability testing, UI testing
Get Started Navigation | Verify navigation to Section 1 introduction. | Test if clicking “Get Started” redirects correctly to Section 1 intro page. | Functional testing
SQL Editor & Query Execution | Validate SQL query input and execution. | Test if user queries are accepted, parsed, and executed against practice DB. | Functional testing, Integration testing
Success Feedback Popup | Ensure correct success message is displayed. | When the correct query is submitted, a popup should appear confirming success. | Functional testing, Usability testing
Hint System | Check hints for incorrect queries. | Test that incorrect queries trigger contextual hints after each wrong attempt. | Functional testing, Error Handling testing
Help Box (after 3 failures) | Ensure help content displays after 3 incorrect attempts. | Verify that the help box appears with simple queries and tutorial links. | Functional testing, Usability testing
Progress Tracking | Verify current level and task saving. | Ensure user’s progress (current task, attempts, completed levels) is stored correctly in DB. | Functional testing, Integration testing
Level Completion & Certificate | Validate reward system. | Test if certificate is emailed after completing 3 tasks, and badge appears in achievements. | Functional testing, Email testing
Achievements View | Ensure badges display correctly. | Verify unlocked achievements appear in the achievements view. | Functional testing, UI testing
Leaderboard | Validate leaderboard ranking system. | Check if scores update correctly and ranks are displayed in real-time. | Functional testing, Performance testing
Database Reset Option | Verify DB reset works. | Ensure that practice DB resets to initial state when reset button is clicked. | Functional testing, Integration testing
Error Handling – Wrong Queries | Ensure errors don’t break the game. | Verify system gracefully handles invalid SQL without crashing. | Error Handling testing
Multi-user Load | Verify system under multiple learners. | Ensure concurrent users can play without performance degradation. | Load testing, Stress testing
Responsiveness | Ensure cross-device compatibility. | Test UI on desktop, tablet, and mobile devices. | Usability testing, Compatibility testing

## Sheet5
Test ID | Feature | Test Case Description | Input Data | Expected Output | Actual Output | Pass/Fail
TC-003 | Auto Intro Scroll | Verify homepage auto-scroll introduces characters | Visit homepage | Character intro displayed with smooth scroll | As expected | Pass
TC-004 | Get Started Redirect | Verify clicking Get Started goes to Section 1 intro | Click button | Redirected to Section 1 | As expected | Pass
TC-005 | Section Intro | Verify characters and story displayed in section intro | Navigate to section | Storyline + dialogues shown | As expected | Pass
TC-006 | Submit SQL Query | Verify correct query execution | SELECT * FROM Hotels; | Success popup | As expected | Pass
TC-007 | Submit SQL Query | Verify incorrect query triggers hint | Wrong SQL query | Hint message displayed | As expected | Pass
TC-008 | Attempt Limit | Verify 3 incorrect attempts trigger help box | 3 wrong queries | Help box appears with tutorial link | As expected | Pass
TC-009 | Reset DB | Verify learner can reset practice DB | Click reset button | DB restored to default state | As expected | Pass
TC-010 | Achievements | Verify learner earns achievement after completing level | Complete Level 1 | Achievement unlocked, badge visible | As expected | Pass
TC-011 | Email Certificate | Verify certificate sent after completing 3 tasks | Complete 3 tasks | Email with certificate delivered | As expected | Pass
TC-012 | View Achievements | Verify learner can view unlocked achievements | Navigate to Achievements | List of earned badges displayed | As expected | Pass
TC-013 | Leaderboard | Verify leaderboard displays correctly | Multiple users with scores | Leaderboard sorted by XP/points | As expected | Pass
TC-014 | Progress Tracking | Verify progress is saved after tasks | Complete 2 tasks | Current level & task updated in DB | As expected | Pass
TC-018 | SQL Injection Prevention | Verify SQL injection is blocked | DROP TABLE Hotels; | Query blocked, error handled | As expected | Pass